Student Record System

Team Execution Playbook

Who does what, in which order, and the exact steps

Software Engineering Mini-Project - Part 2 (backlog, Sprint 1, Sprint 2)

Document ID: PB-SRSYS-01     |     Version 1.0     |     12 October 2026

TEAM-E12

Team Members

Monika PM - PES1UG24CS275

Kushita K - PES1UG24CS247

Nagashree R Patil - PES1UG24CS289

Nidhi L - PES1UG24CS298

# How to Read This Document

This playbook turns the teacher's Part-2 instructions into a day-by-day plan for four people. Each member should read Sections 1 to 6 once, then work from their own task cards in Section 7. It is based on the backlog plan v2 (45 issues, 146 story points: Sprint 1 = 64, Sprint 2 = 82). If the team changes points or owners, update Section 3 and the matching cards.

| Section | What it contains | Who reads it |
| --- | --- | --- |
| 1 | How to upload this document to your own Claude account and the exact prompts to paste | Everyone |
| 2 | The teacher's Part-2 rules turned into a checklist with owners and dates | Everyone |
| 3 | Who owns what, backups, and which files each person owns | Everyone |
| 4 | Technical ground rules: stack, folders, API conventions, git and PR steps, Definition of Done | Everyone |
| 5 | Calendar: dry-run week, Sprint 1 and Sprint 2, day by day for each person | Everyone |
| 6 | Hand-off map: who must finish what before whom | Everyone |
| 7 | Task cards for every issue: steps, done-when, test case, what it unblocks | Each member reads their own part |
| 8 | Team lead checklists (Monika) | Monika |
| 9 | Demo video scripts (1 minute and 2 minutes) | Nidhi, Monika |
| 10, 11 | Deviations log and risks with fallbacks | Everyone |
| Appendices | A API contract, B database tables, C test cases, D templates (PR template, CI file, standup message) | As needed |

# 1. Using This Document With Your Own Claude Account

## 1.1 Setup (5 minutes, each member)

1. Save this playbook, the submitted SRS, the SAD (Architecture and Design Specification) and the Test Plan on your computer. Claude does not know our project unless you give it these four files.

2. Open your own Claude account and start a new chat (or a new Project if your plan has Projects, so the files stay available). Attach all four documents.

3. Paste the Master Prompt from Section 1.2, then paste your personal first message from the start of your own part of Section 7.

4. Work on ONE task card at a time. Copy the card's steps and 'Done when' text into the chat. Ask Claude for: the list of files, the full code, unit tests, how to run and test it, and the commit message and PR description.

5. Run the code yourself, test it using the card's 'Done when' line, then follow the git steps in Section 4.4. Do not merge anything you have not run.

6. Start a fresh chat each day and re-attach the four documents so Claude has the full context.

## 1.2 Master Prompt (everyone pastes this first)

You are my pair-programming assistant for our Software Engineering

mini-project "Student Record System" (TEAM-E12, four students).

I attached: (1) the Team Execution Playbook, (2) our SRS, (3) our SAD,

(4) our Test Plan. These are the source of truth.

Rules:

- Stack: React + Vite (frontend), Node.js + Express (backend), PostgreSQL.

Folder structure, API conventions, error format and git workflow are in

Section 4 of the Playbook. Follow them exactly.

- Implement exactly the "Steps" and "Done when" of the task card I give

you. Do not add extra features.

- Work on one task at a time. For each task give me:

(a) files to create or change, (b) full code, (c) unit tests,

(d) how to run and test it (curl or UI steps), (e) a commit message

and a PR description that contains "Closes #<issue number>".

- Do not change files owned by another member (Section 3.3). If you need a

change there, tell me what to ask that person.

- Use parameterised SQL, validate all input on the server, and write grade

and attendance changes inside a database transaction.

- If anything conflicts with the SRS, SAD or Test Plan, tell me clearly so I

can add it to docs/DEVIATIONS.md.

- Explain the code briefly so I can answer questions about it in the demo.

First, summarise my task list and the order I should do it, then wait.

## 1.3 Rules for using AI on this project

- The teacher allows GPTs. You are still the author of your PR: run it, read it, and be able to explain every file in the final demo.

- Never paste real passwords, tokens or .env contents into Claude. Use the test accounts in the README (password Test@1234).

- If Claude suggests a different library, route or table name, stay with this playbook so the four parts fit together.

- Commit with your own GitHub account and your own words in commit messages.

# 2. The Teacher's Part-2 Rules as a Checklist

| Teacher's instruction | How we do it | Owner | When |
| --- | --- | --- | --- |
| 1a Create a Project and link it with the mini-project repo | Project 'Student Record System - TEAM-E12' linked on the repo's Projects tab; visible to the instructor | Monika | Mon 12 Oct |
| 1b Backlog from FRs and NFRs in the SRS | 39 existing issues kept, 6 new added (45) | Monika | Mon 12 Oct |
| 1c Story points on every item | Points from the plan v2 spreadsheet (Sprint 1 = 64, Sprint 2 = 82) | Monika, team agrees | Mon 12 Oct |
| 1d Assign stories to team members | Section 3.1. Teammates must be repo collaborators first | Monika | Mon 12 Oct |
| 1e Plan two sprints | Sprint field set to Sprint 1 or Sprint 2 on every issue | Monika | Mon 12 Oct |
| 1f Dry run 12-16 Oct | Section 5.1 | All | 12-16 Oct |
| 1g Backlog can change on 19 Oct | Final edits Monday morning only | Monika | Mon 19 Oct |
| 2a Complete Sprint 1 items | Section 5.2 and cards | All | 19-23 Oct |
| 2b Enable GitHub Actions | DEV-01 | Nagashree | Mon 19 Oct |
| 2c Assigned member raises the PR | Rule 4.4: one PR per issue, raised by the assignee | Each owner | Every task |
| 2d Repo owner reviews and merges | Monika reviews within 24 h and merges. Kushita reviews Monika's PRs | Monika, Kushita | Every PR |
| 2e GPTs allowed | Claude, using Section 1 | All | - |
| 2f Follow SRS, SAD and Test Plan | Every card names the requirement and test case | All | - |
| 2g Record a 1-minute video of a working product | DEV-05, script in Section 9.1 | Nidhi | Fri 23 Oct |
| 2h Upload it to the repo | demo/sprint1.mp4 through a PR | Nidhi | Fri 23 Oct |
| 2i Deviations documented, explained at final demo | docs/DEVIATIONS.md kept live, DEV-07 | Monika, all | From 19 Oct |
| 3a Complete Sprint 2 items | Section 5.3 and cards | All | 26-30 Oct |
| 3b Record a 2-minute video of a working product | DEV-06, script in Section 9.2 | Nidhi | Fri 30 Oct |
| 3c Complete the documentation | DEV-03 and DEV-07 | Nidhi, Monika | Fri 30 Oct 3 PM |
| 3d Freeze the development cycle | DEV-08 and tag v1.0 | Monika | Fri 30 Oct 5 PM |

# 3. Team, Roles and Ownership

## 3.1 Who does what

| Member | Role | Sprint 1 issues (points) | Sprint 2 issues (points) | Total |
| --- | --- | --- | --- | --- |
| Monika (team lead) | Security core, audit, reviews, release | SEC-04 (3), SEC-02 (5), SEC-01 (3), FR-01 (5) = 16 | FR-16 (5), SEC-07 (2), SEC-05 (3), SEC-06 (5), SEC-09 (3), DEV-07 (2), DEV-08 (1) = 21 | 37 |
| Kushita | Project setup, admin features, deployment, performance | DEV-04 (3), FR-02 (5), FR-03 (3), FR-04 (3), FR-05 (3) = 17 | FR-15 (5), NFR-04 (2), NFR-08 (3), SEC-03 (3), NFR-03 (2), NFR-01 (3), NFR-02 (2) = 20 | 37 |
| Nagashree | Faculty features, CI, notifications, testing | DEV-01 (3), FR-06 (5), FR-08 (5), FR-09 (2) = 15 | FR-07 (2), FR-13 (5), NFR-09 (2), NFR-06 (2), NFR-07 (5), DEV-02 (5) = 21 | 36 |
| Nidhi | Front-end shell, student/parent portal, reports, docs, videos | UI-01 (5), SEC-08 (3), FR-10 (3), FR-17 (3), DEV-05 (2) = 16 | FR-14 (5), FR-11 (2), FR-12 (3), NFR-05 (2), NFR-10 (3), DEV-03 (3), DEV-06 (2) = 20 | 36 |

Totals: Sprint 1 = 64, Sprint 2 = 82, project = 146 story points.

## 3.2 Backup owners

If someone is ill or stuck for more than a day, the backup takes over their open issues and tells Monika, who updates the Assignee on the board. Pairs: Monika and Kushita, Nagashree and Nidhi.

## 3.3 File ownership (stops merge conflicts)

Only the owner edits these files. If you need a change in someone else's file, ask them in the group chat or open a small PR and tag them.

| Owner | Files and folders |
| --- | --- |
| Monika | backend/src/middleware/auth.js, rbac.js, validate.js, rateLimit.js, audit.js; backend/src/utils/jwt.js, password.js; routes auth.routes.js, audit.routes.js; docs/CONTRACTS.md, docs/DEVIATIONS.md |
| Kushita | db/*, scripts/*, backend/src/app.js, backend/src/config/*; routes students.routes.js, faculty.routes.js, courses.routes.js, grievances.routes.js; frontend/src/pages/admin/*; deployment files |
| Nagashree | routes grades.routes.js, attendance.routes.js, student-attendance.routes.js, notifications.routes.js, settings.routes.js; services grade.js, attendance.js, notification.js; .github/*; frontend/src/pages/faculty/*; docs/api/openapi.yaml; docs/test-results.md |
| Nidhi | frontend/src (layout, auth context, api client, router, config/menu.js, pages/student/*, pages/parent/*); backend/src/middleware/ownership.js; routes student-records.routes.js, parents.routes.js, reports.routes.js; services/export.js; README.md and user guide; demo/* |
| Shared rule | package.json and package-lock.json are conflict-prone: add a dependency in its own small commit, pull main first, and tell the group. Nobody except Kushita edits app.js because every router is registered in DEV-04. |

# 4. Technical Ground Rules

## 4.1 Stack (follows the SAD)

- Frontend: React with Vite, react-router-dom. Backend: Node.js 20 with Express. Database: PostgreSQL. Auth: bcrypt + JWT. Tests: Jest (backend) with Supertest for API tests. PDF: pdfkit. Email: Nodemailer with a sandbox SMTP (Mailtrap).

- Change the stack only if the whole team agrees, and then add an entry to the deviations log.

## 4.2 Repository structure

backend/

src/app.js

src/config/            (db.js, env.js)

src/middleware/        (auth, rbac, ownership, validate, rateLimit, audit, errorHandler)

src/routes/            (auth, students, student-records, student-attendance,

faculty, courses, grades, attendance, parents,

notifications, settings, reports, grievances, audit)

src/services/          (grade, attendance, notification, export)

src/utils/             (jwt, password, response)

tests/

frontend/

src/config/menu.js     (one menu list per role)

src/pages/admin|faculty|student|parent/

src/api/client.js  src/auth/AuthContext.jsx  src/components/

db/        schema.sql  seed.sql  migrations/

scripts/   backup.sh  restore.sh  generate-load-data.js

docs/      SRS, SAD, TestPlan, CONTRACTS.md, DEVIATIONS.md, api/openapi.yaml,

test-results.md, perf/, security/, test-evidence/

demo/      sprint1.mp4  sprint2.mp4

.github/   workflows/ci.yml  pull_request_template.md

README.md  .env.example

## 4.3 API and error conventions

- Base path /api/v1. JSON only. JWT in the header 'Authorization: Bearer <token>'. Roles: ADMIN, FACULTY, STUDENT, PARENT. JWT payload: { sub (user id), role, exp (30 minutes) }.

- Success response: { "success": true, "data": {...}, "meta": {...} }. Error response: { "success": false, "error": { "code": "VALIDATION_ERROR", "message": "..." } }.

- Status codes: 400 validation, 401 not logged in or bad token, 403 wrong role or not your record, 404 not found, 409 duplicate, 423 account locked, 429 too many requests, 500 unexpected (generic message, details only in the server log).

- Every write endpoint uses parameterised SQL, server-side validation and (for grades and attendance) a database transaction.

## 4.4 Git and pull request steps (every task)

git checkout main

git pull

git checkout -b feature/FR-06-enter-marks        # feature/<ISSUE-ID>-short-name

# ... write code and tests, commit often ...

git add .

git commit -m "FR-06: validate marks and compute letter grade (#7)"

git push -u origin feature/FR-06-enter-marks

Then on GitHub: open a Pull Request into main. Title: the issue title (for example 'FR-06: Enter marks and compute letter grades'). Description: use the template and include 'Closes #7'. Check that CI is green, request a review from Monika (from Kushita if the PR is Monika's) and fix comments. Monika merges using 'Squash and merge'. Never push directly to main.

## 4.5 Board status

- To Do to In Progress: when you create your branch. In Review: when you open the PR. Done: when it is merged (the 'Closes #n' line closes the issue).

- One PR per issue, kept small. Pull main before you start each task.

## 4.6 Definition of Done (every PR)

- The 'Done when' line of the card is met and you tested it by hand.

- Unit tests are added and CI is green.

- SQL is parameterised, input is validated on the server, grade and attendance writes use a transaction.

- No secrets or passwords in the code. The PR description shows evidence (curl output or screenshot).

- Anything that differs from the SRS, SAD or Test Plan is added to docs/DEVIATIONS.md.

## 4.7 Daily routine

- 10-minute standup at a fixed time (agree it on Fri 16 Oct). Each person posts: done yesterday, doing today, blocked by whom (message in Appendix D).

- Review PRs within 24 hours. Merge before 6 PM so the next person can pull.

- If you are blocked for more than 2 hours, message the person named in 'Start only after' and Monika.

# 5. Calendar: Day by Day

Today is Monday 12 October 2026. Do not do Sprint 1 issue work before Monday 19 October: the commit and PR dates must fall inside the sprint week.

## 5.1 Dry-run week (12 - 16 October)

| Day | Monika | Kushita | Nagashree | Nidhi |
| --- | --- | --- | --- | --- |
| Mon 12 | Finish the backlog on GitHub (Section 8.1): collaborators, titles, new issues, points, sprints, owners, link project to repo, branch protection on main. | Accept the invitation. Install Node 20, PostgreSQL, Git, VS Code. Clone the repo. Read SAD Sections 3, 9, 11. | Same setup. Read Test Plan TC-05 to TC-07 and SAD Sections 8 to 10. | Same setup. Read SRS FR-10, FR-11, FR-12, FR-17 and SAD Sections 8 to 10. |
| Tue 13 | Write docs/CONTRACTS.md (JWT payload, roles, error codes), .env.example and the PR template. Review Kushita's draft PR. | DEV-04: folders, backend, frontend, schema.sql, seed.sql, health endpoint, empty routers. Open the PR. | Write the CI workflow on a branch (do not merge yet). Read FR-06, FR-08, FR-09 acceptance criteria. | Sketch the 4 dashboards and the screen list. Learn the React Router layout. |
| Wed 14 | Review and merge DEV-04. Check it runs from a fresh clone. | Fix review comments. Check the seed data (1 admin, 2 faculty, 5 students, 1 parent, 3 courses). | Pull main and run backend and frontend. Check the health endpoint and seed. | Pull main and run it. Check the seed data and the empty frontend. |
| Thu 15 | Merge each practice PR. Kushita approves Monika's. | Practice PR: add your name and role to docs/TEAM.md using the branch, commit and PR rules. | Practice PR (same). | Practice PR (same). |
| Fri 16 | 30-minute review call: can everyone clone, run, branch, PR and merge? Fix process problems. Set the standup time. | Confirm Sprint 1 tasks with Claude (Section 1). | Confirm Sprint 1 tasks with Claude. | Confirm Sprint 1 tasks with Claude. |
| Sat-Sun | Rest. Backlog edits are still allowed. | Rest. | Rest. | Rest. |

## 5.2 Sprint 1 (19 - 23 October): login, admin data, grades, attendance, student view

| Day | Monika | Kushita | Nagashree | Nidhi |
| --- | --- | --- | --- | --- |
| Mon 19 | SEC-04 JWT (PR 2 PM). SEC-02 role middleware (merged by 6 PM). Review PRs. Final backlog edits (morning). | FR-02 create student: model and validation in the morning, add requireRole after 6 PM. | DEV-01 CI (PR by noon). Then FR-06 logic and tests (letter grade, validation). | UI-01 part 1: router, auth context, API client, login page on a mock. |
| Tue 20 | SEC-01 password utility (merged by noon). FR-01 login, me, change-password (PR by 5 PM). Login JSON to Nidhi (Mon evening). | FR-03 update and deactivate. FR-04 faculty accounts after Monika's noon merge. | FR-06 endpoint (transaction) and Enter Marks page. | UI-01 part 2: menu config, four dashboards, change-password page. SEC-08 ownership helper. Shell merged by 6 PM. |
| Wed 21 | Review and merge. Test login end to end with Nidhi's UI. Fix bugs. | FR-05 courses, assign faculty, enrol. Admin pages. | FR-08 attendance (24 h edit rule) and Mark Attendance page. | Switch login to the real API. FR-10 backend and student pages (seed data if FR-06 and FR-08 are not yet merged). |
| Thu 22 | Merge all. Smoke-test the demo flow. Update README run steps. Update the deviations log. | Admin UI polish. Manual tests TC-03 and TC-04. Bug fixes. | FR-09 attendance percentage. Tests TC-05, TC-06, TC-07. | FR-17 profile update. Connect FR-10 to real data. Test TC-08. |
| Fri 23 | 12 noon: freeze. Final merge, tag sprint-1, clean-clone check, update board statuses. | 12 noon: freeze. Bug fixes only. Update statuses. Screenshot of CI green. | 12 noon: freeze. Bug fixes only. Update statuses. | After noon: record and upload the 1-minute video (DEV-05). |

## 5.3 Sprint 2 (26 - 30 October): audit, security, reports, notifications, quality, documentation, freeze

| Day | Monika | Kushita | Nagashree | Nidhi |
| --- | --- | --- | --- | --- |
| Mon 26 | 10 AM message: add the req.audit line to every write endpoint. FR-16 audit log (middleware, API, admin page). | FR-15 grievances. Add the req.audit line. | FR-07 correct marks with reason. Start FR-13. Add the req.audit line. | FR-14: export module PR first (Mon evening), then report endpoints. Add the req.audit line. |
| Tue 27 | SEC-07 append-only audit table. SEC-05 account lockout. | NFR-04 deploy and monitor. NFR-08 backup and restore. | Finish FR-13 notifications. NFR-09 integrity test. | Finish FR-14 report pages. FR-11 report-card PDF. Start FR-12. |
| Wed 28 | SEC-06 validation, queries, ZAP scan and fixes. | SEC-03 HTTPS. NFR-03 large data set and indexes. | NFR-07 tests to 70 % and OpenAPI file. NFR-06 browser check. | FR-12 parent view. Start accessibility and usability checks. 6 PM: FEATURE COMPLETE, no new features after this. |
| Thu 29 | SEC-09 rate limiting. DEV-07 deviations document. Re-run ZAP. | NFR-01 JMeter run. NFR-02 report timing. Fix performance issues. | DEV-02: run TC-01 to TC-17 and record results. Raise bug issues. | NFR-05 usability. NFR-10 accessibility. Start DEV-03 documentation. Fix bugs. |
| Fri 30 | Merge final fixes. DEV-08: freeze at 5 PM, tag v1.0, clean-clone check. | Fix bugs by noon. Give final results to Nagashree and Nidhi. | Retest fixes. Final statuses in the log. | Finish DEV-03 by 3 PM. Record and upload the 2-minute video (DEV-06). |

# 6. Hand-Off Map: Who Must Finish What Before Whom

This is the list of promises between team members. If you will miss a time, tell the person waiting before the deadline.

| # | Needed first | Provided by | Needed by | Who waits | If late |
| --- | --- | --- | --- | --- | --- |
| 1 | DEV-04 project skeleton, schema, seed, empty routers | Kushita | Wed 14 Oct | Everyone | Monika helps Kushita the same day |
| 2 | SEC-04 JWT and SEC-02 requireRole merged | Monika | Mon 19 Oct, 6 PM | Kushita, Nagashree, Nidhi | Use a temporary dev-only role header and remove it before the Friday freeze |
| 3 | Login request and response JSON | Monika | Mon 19 Oct evening | Nidhi | Nidhi follows CONTRACTS.md |
| 4 | SEC-01 password utility | Monika | Tue 20 Oct, noon | Kushita (FR-04) | Kushita starts with the other endpoints first |
| 5 | FR-01 login endpoint | Monika | Tue 20 Oct, 5 PM | Nidhi (real login) | Keep the mock until merged |
| 6 | UI-01 shell and menu config | Nidhi | Tue 20 Oct, 6 PM | Kushita, Nagashree (pages) | They build backend first and add pages Wed |
| 7 | SEC-08 ownership helper | Nidhi | Tue 20 Oct | Nidhi (FR-10), Kushita (GET student) | Kushita adds the check after the merge |
| 8 | FR-06 marks and FR-08 attendance merged | Nagashree | Wed 21 Oct, 6 PM | Nidhi (FR-10 real data) | Nidhi uses seed data |
| 9 | FR-09 attendance-summary endpoint | Nagashree | Thu 22 Oct, noon | Nidhi (My Attendance) | Nidhi shows grades first |
| 10 | Every owner adds the req.audit line | Each owner | Mon 26 Oct, 6 PM | Monika (FR-16 test) | Monika adds it herself in a PR |
| 11 | FR-14 export module | Nidhi | Mon 26 Oct evening | Nidhi (FR-11), Kushita (NFR-02) | - |
| 12 | FR-09 percentage (done in Sprint 1) | Nagashree | Mon 26 Oct | Nagashree (FR-13) | - |
| 13 | NFR-04 deployment | Kushita | Tue 27 Oct | Kushita (SEC-03, NFR-01), Monika (ZAP) | Run locally and log a deviation |
| 14 | Feature complete | All | Wed 28 Oct, 6 PM | Nagashree (DEV-02), Nidhi (DEV-03), Kushita (NFR-01) | Nagashree tests what exists and lists the rest as blocked |
| 15 | DEV-02 results and DEV-07 deviations | Nagashree, Monika | Thu 29 Oct evening | Nidhi (DEV-03) | - |
| 16 | DEV-03 docs and DEV-06 video | Nidhi | Fri 30 Oct, 3 PM | Monika (DEV-08) | - |

# 7. Task Cards

Each card is one GitHub issue. Copy a card into your Claude chat when you start that task. 'Start only after' tells you what must be merged first.

## 7.1 Monika (team lead)

Sprint 1: SEC-04 (3), SEC-02 (5), SEC-01 (3), FR-01 (5) = 16 SP.   Sprint 2: FR-16 (5), SEC-07 (2), SEC-05 (3), SEC-06 (5), SEC-09 (3), DEV-07 (2), DEV-08 (1) = 21 SP.

Your first message to Claude (after the Master Prompt):

I am Monika, team lead of TEAM-E12. I attached the Team Playbook, SRS, SAD and Test Plan. My tasks are in Section 7.1. Start with SEC-04 (JWT) and SEC-02 (role-based access) for Monday 19 Oct. Give me the files, code, tests, how to run them, and the commit message and PR description.

### Your recurring duties as team lead

- Review each PR within 24 hours (checklist in Section 8.2) and merge it before 6 PM. Kushita reviews your own PRs.

- Keep the board correct (statuses, assignees) and run the standup.

- Keep docs/DEVIATIONS.md updated every Thursday and Friday of each sprint.

### Monika - Sprint 1 task cards

### SEC-04 - Implement Secure JWT Session Management

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 1 / 3 SP |
| GitHub issue | #32 |
| When | Mon 19 Oct, morning. PR by 2 PM, merged by 6 PM. |
| Start only after | DEV-04 skeleton merged (14 Oct). |
| Steps | 1. Create backend/src/utils/jwt.js with signToken({ sub, role }) (expires in 30 minutes) and verifyToken(token). Read JWT_SECRET from .env (never commit it). 2. Create backend/src/middleware/auth.js. authenticate reads 'Authorization: Bearer <token>', sets req.user = { id, role }, and returns 401 (error envelope) when the token is missing, expired or tampered. 3. Write unit tests for valid, expired, tampered and missing tokens. 4. Open the PR 'SEC-04: Implement secure JWT session management' with 'Closes #32'. |
| Done when | Expired or tampered token returns HTTP 401. Secret is only in .env. Tests pass in CI. |
| Test case(s) | TC-16 |
| Unblocks | Every protected endpoint (all members). |

### SEC-02 - Enforce Server-Side Role-Based Access Control

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 1 / 5 SP |
| GitHub issue | #30 |
| When | Mon 19 Oct, right after SEC-04. Merged by 6 PM. |
| Start only after | SEC-04 (same day). |
| Steps | 1. Create backend/src/middleware/rbac.js with requireRole(...roles) and constants ADMIN, FACULTY, STUDENT, PARENT. Return 403 FORBIDDEN when req.user.role is not allowed. 2. Write docs/CONTRACTS.md: a table of which role may call which endpoint (copy it from Appendix A of this playbook) plus the JWT payload and error codes. 3. Apply requireRole to all route stubs created in DEV-04 so nobody can forget it. 4. Add tests: for each role, call one endpoint it may use and one it may not. 5. Post in the group chat that the middleware is merged and how to use it: router.post('/', authenticate, requireRole(ADMIN), handler). |
| Done when | A wrong role gets 403 on every protected route. The role table in CONTRACTS.md matches Appendix A. |
| Test case(s) | TC-06 |
| Unblocks | FR-02 to FR-17 and SEC-08. |

### SEC-01 - Enforce Secure Password Storage and Validation

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 1 / 3 SP |
| GitHub issue | #29 |
| When | Tue 20 Oct, morning. Merged by 12 noon. |
| Start only after | DEV-04. |
| Steps | 1. Create backend/src/utils/password.js with hashPassword (bcrypt, cost 10 or higher), comparePassword and validatePasswordRules (at least 8 characters with upper case, lower case and a digit). 2. Check that the seed users in db/seed.sql store bcrypt hashes (test account password: Test@1234) and list the test accounts in the README. 3. Make sure no password or hash is ever written to logs or returned by an API. 4. Unit tests: weak passwords rejected, the hash differs from the plain text, compare works. |
| Done when | The database holds only bcrypt hashes. Weak passwords are rejected with HTTP 400. |
| Test case(s) | TC-01 |
| Unblocks | FR-01 (Monika) and FR-04 (Kushita needs it by Tue noon). |

### FR-01 - User Authentication and Role-Based Access

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 1 / 5 SP |
| GitHub issue | #1 |
| When | Tue 20 Oct. PR by 5 PM. |
| Start only after | SEC-04 and SEC-01 merged. |
| Steps | 1. Create routes/auth.routes.js plus controller and service. POST /api/v1/auth/login (body: username, password) returns { token, role, name, mustChangePassword } or 401 with a generic message that never says which part was wrong. 2. Add GET /api/v1/auth/me (current user) and POST /api/v1/auth/change-password (current and new password, applies the SEC-01 rules, clears must_change_password). 3. On a failed login increase users.failed_attempts. The lockout itself is SEC-05 in Sprint 2. 4. Send Nidhi the exact request and response JSON by Mon evening so the login page can be built against a mock first. 5. Integration test: log in with all four seeded roles; a wrong password returns 401. |
| Done when | Valid credentials return a JWT and the role within 2 seconds. Invalid credentials return an error and no token. |
| Test case(s) | TC-01 |
| Unblocks | Nidhi's login page integration (Wed 21) and all manual testing. |

### Monika - Sprint 2 task cards

### FR-16 - Maintain Audit Log for Data Changes

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 2 / 5 SP |
| GitHub issue | #17 |
| When | Mon 26 Oct. |
| Start only after | Sprint 1 write endpoints exist (students, faculty, courses, grades, attendance). |
| Steps | 1. Create middleware/audit.js. After a successful create, update or delete it reads req.audit = { entity, entityId, old, new } and inserts a row in audit_log (user id, role, action, entity, entity_id, old_value, new_value, timestamp). 2. Post in the group chat on Mon 26 Oct by 10 AM: every owner adds ONE line (req.audit = {...}) in each of their write endpoints. Each owner does this in a small PR the same day (10 minutes each). 3. GET /api/v1/audit-logs (ADMIN only, filter by date and entity) and an admin page 'Audit Log'. 4. Tests: update a grade and check the entry has the old and new value, user and timestamp. |
| Done when | Every create, update and delete on student, grade and attendance data produces an audit entry. The UI has no edit or delete for entries. |
| Test case(s) | TC-14 |
| Unblocks | SEC-07. |

### SEC-07 - Enforce Append-Only Audit Log and Retention

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 2 / 2 SP |
| GitHub issue | #35 |
| When | Tue 27 Oct. |
| Start only after | FR-16. |
| Steps | 1. Add db/migrations/audit_append_only.sql: create the application database user with INSERT and SELECT only on audit_log (REVOKE UPDATE, DELETE). Document how to apply it in the README. 2. Make sure no PUT, PATCH or DELETE route exists for audit logs. 3. Write the retention rule (keep for at least 1 year, no purge job) in docs/CONTRACTS.md. 4. Test: DELETE /api/v1/audit-logs/1 returns 403 or 405, and a direct UPDATE with the app user fails. |
| Done when | Audit entries cannot be edited or deleted through the application. |
| Test case(s) | TC-14 |
| Unblocks | - |

### SEC-05 - Implement Account Lockout After Failed Logins

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 2 / 3 SP |
| GitHub issue | #33 |
| When | Tue 27 Oct. |
| Start only after | FR-01. |
| Steps | 1. In the login service: when failed_attempts reaches 5, set locked_until = now + 15 minutes. While locked, return HTTP 423 'account locked'. 2. A correct login after the lock expires resets failed_attempts to 0. 3. Tests: 5 wrong passwords then the correct one is still rejected with 423; after the lock time passes it works. |
| Done when | After 5 consecutive failed logins an account is locked for 15 minutes. |
| Test case(s) | TC-02 |
| Unblocks | - |

### SEC-06 - Prevent SQL Injection and Cross-Site Scripting

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 2 / 5 SP |
| GitHub issue | #34 |
| When | Wed 28 Oct. |
| Start only after | Most endpoints merged (Mon and Tue). |
| Steps | 1. Create middleware/validate.js using a schema library (Joi or zod) and add a schema for every write endpoint. Ask each owner to review the schema for their endpoint. 2. Search the code for any SQL built by string concatenation and replace it with parameterised queries. 3. Check the frontend never uses dangerouslySetInnerHTML and that user text (grievances, names) is shown as plain text. 4. Run an OWASP ZAP baseline scan against the local app, fix every High or Critical finding, save the report in docs/security/. |
| Done when | No SQL injection or script execution is possible. ZAP shows no High or Critical findings. |
| Test case(s) | TC-15 |
| Unblocks | - |

### SEC-09 - Implement API Rate Limiting

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 2 / 3 SP |
| GitHub issue | #37 |
| When | Thu 29 Oct. |
| Start only after | - |
| Steps | 1. Add express-rate-limit: 100 requests per minute per IP on /api/v1; excess requests get HTTP 429 in the error envelope. 2. Write scripts/rate-limit-test.sh (or .js) that sends 150 requests in one minute. 3. Record the result in the test log. |
| Done when | Requests above 100 per minute from one client get HTTP 429. |
| Test case(s) | TC-17 |
| Unblocks | - |

### DEV-07 - Document Deviations from SRS, SAD and Test Plan

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 2 / 2 SP |
| GitHub issue | NEW (number given when created) |
| When | Thu 29 Oct (the log is kept up to date from 19 Oct). |
| Start only after | Features complete (Wed 28 Oct). |
| Steps | 1. Collect every entry from docs/DEVIATIONS.md (template in Appendix D, starting list in Section 10). 2. Ask each member to confirm their own entries by Thu noon. 3. For each deviation write: document and section, what was submitted, what was built, why, impact. Put a one-page summary at the top. 4. Mark the file as final on Fri 30 Oct. |
| Done when | Every difference between the built product and the submitted SRS, SAD and Test Plan is listed with a reason. |
| Test case(s) | Part-2 Sprint 1(i) |
| Unblocks | Final demo. |

### DEV-08 - Freeze Development and Tag v1.0 Release

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Monika / Sprint 2 / 1 SP |
| GitHub issue | NEW (number given when created) |
| When | Fri 30 Oct, 5 PM. |
| Start only after | All PRs merged, CI green, DEV-03 and DEV-06 done. |
| Steps | 1. Check the Project board: every issue is Done or has a written reason in DEVIATIONS.md. 2. Clone the repo into a new folder and run it from the README one more time. 3. Protect main fully (no direct pushes, no new merges). Tag: git tag -a v1.0 -m 'Final submission' and git push origin v1.0. Create a GitHub Release with short notes. 4. Take screenshots of the Project board and the green CI for the submission. |
| Done when | Development is frozen and tagged v1.0. |
| Test case(s) | Part-2 Sprint 2(d) |
| Unblocks | Final submission and demo. |

## 7.2 Kushita

Sprint 1: DEV-04 (3), FR-02 (5), FR-03 (3), FR-04 (3), FR-05 (3) = 17 SP.   Sprint 2: FR-15 (5), NFR-04 (2), NFR-08 (3), SEC-03 (3), NFR-03 (2), NFR-01 (3), NFR-02 (2) = 20 SP.

Your first message to Claude (after the Master Prompt):

I am Kushita from TEAM-E12. I attached the Team Playbook, SRS, SAD and Test Plan. My tasks are in Section 7.2. Start with DEV-04 (project skeleton, database schema and seed data). Give me the folder structure, all files, commands to run, and the commit message and PR description.

### Kushita - Sprint 1 task cards

### DEV-04 - Set Up Project Skeleton, Database Schema and Seed Data

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 1 / 3 SP |
| GitHub issue | NEW (number given when created) |
| When | Tue 13 Oct to Wed 14 Oct (dry-run week). PR open Tue, merged Wed. |
| Start only after | Backlog finalised (Mon 12 Oct). |
| Steps | 1. Create the folder structure from Section 4.2: backend (Node.js + Express), frontend (React + Vite), db, docs, scripts, .github. 2. Backend: package.json, src/app.js, config/db.js (pg Pool), response envelope helper, central errorHandler, GET /api/v1/health, and one EMPTY router file per route group listed in Section 4.2, all already registered in app.js. This means nobody else needs to edit app.js. 3. Frontend: Vite React app with react-router-dom and an api/client.js stub. 4. db/schema.sql with all tables from Appendix B and db/seed.sql with 1 admin, 2 faculty, 5 students, 1 parent linked to 1 student, 3 courses and enrolments. Use a precomputed bcrypt hash of Test@1234 for every account. 5. Add .env.example, README with run instructions (install, create database, run schema and seed, npm run dev) and an npm script 'db:reset'. 6. Open the PR. Monika reviews and merges on Wed 14 Oct. |
| Done when | A fresh clone runs with npm install and npm run dev. GET /api/v1/health returns success. The seed loads without errors. |
| Test case(s) | Setup (no TC) |
| Unblocks | Everyone. Nobody can start Sprint 1 work without this. |

### FR-02 - Create Student Records

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 1 / 5 SP |
| GitHub issue | #2 |
| When | Mon 19 Oct. Start the model and validation in the morning and add requireRole after Monika's merge (6 PM). |
| Start only after | DEV-04. SEC-04 and SEC-02 for the role check. |
| Steps | 1. POST /api/v1/students (ADMIN): roll_no, name, dob, department, semester, guardian_contact, phone, email, address. Validate every mandatory field. A duplicate roll_no returns 409. 2. GET /api/v1/students (list with search by roll_no or name) and GET /api/v1/students/:id. 3. Admin pages: 'Students' list with search and an 'Add Student' form. Put them under frontend/src/pages/admin/ and add the menu item in the admin menu config (created by Nidhi in UI-01; until then keep it as a standalone page). 4. Unit tests for validation and the duplicate case. |
| Done when | Record is saved and searchable within 2 s. A duplicate roll number is rejected with an error message. All mandatory fields are validated. |
| Test case(s) | TC-03 |
| Unblocks | FR-03, FR-05, and the data Nagashree and Nidhi use. |

### FR-03 - Update and Deactivate Student Records

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 1 / 3 SP |
| GitHub issue | #4 |
| When | Tue 20 Oct. |
| Start only after | FR-02. |
| Steps | 1. PUT /api/v1/students/:id to update fields (keep roll_no unique). 2. PATCH /api/v1/students/:id/deactivate sets is_active = false (soft delete). The row is never removed. 3. Deactivated students are hidden from the default list. 4. UI: edit form and a 'Deactivate' button with a confirmation dialog. 5. Tests: update, deactivate, and that the row still exists. |
| Done when | Updates are visible immediately. A deactivated student is hidden from lists but the record stays in the database. |
| Test case(s) | TC-03 |
| Unblocks | - |

### FR-04 - Manage Faculty Accounts

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 1 / 3 SP |
| GitHub issue | #5 |
| When | Tue 20 Oct (after Monika merges SEC-01 at noon) to Wed 21 Oct. |
| Start only after | SEC-01 (password utility). |
| Steps | 1. POST /api/v1/faculty (ADMIN): creates a users row (role FACULTY) and a faculty row. Generate a temporary password, hash it with the SEC-01 utility, set must_change_password = true. Show the temporary password to the admin once. 2. PATCH /api/v1/faculty/:id (edit) and PATCH /api/v1/faculty/:id/deactivate. 3. Admin pages: faculty list and create form. 4. The forced password change at first login is handled by the login response (mustChangePassword) and Nidhi's change-password page. Test it together on Wed. |
| Done when | A new Faculty user can log in with the temporary password and is forced to change it at first login. |
| Test case(s) | TC-04 |
| Unblocks | FR-05 (assigning faculty). |

### FR-05 - Create Courses and Assign Faculty

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 1 / 3 SP |
| GitHub issue | #6 |
| When | Wed 21 Oct. |
| Start only after | FR-04. |
| Steps | 1. POST /api/v1/courses (code, name, semester). PUT /api/v1/courses/:id/faculty assigns the faculty member (the SAD schema has one faculty_id per course, see Section 10). 2. POST /api/v1/courses/:id/enrolments to enrol students. 3. GET /api/v1/courses: ADMIN sees all, FACULTY sees only the courses assigned to them. 4. Admin pages: course list, create form, assign faculty, enrol students. |
| Done when | A Faculty user sees only the courses assigned to him or her. |
| Test case(s) | TC-04 |
| Unblocks | Realistic data for Nagashree's pages. |

### Kushita - Sprint 2 task cards

### FR-15 - Raise and Resolve Student Grievances

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 2 / 5 SP |
| GitHub issue | #16 |
| When | Mon 26 Oct. |
| Start only after | FR-06 and FR-08 (grades and attendance exist). |
| Steps | 1. POST /api/v1/grievances (STUDENT): target_type (grade or attendance), target_id, reason. GET /api/v1/grievances (student sees own, faculty sees those on their courses). PATCH /api/v1/grievances/:id (FACULTY): response and status Open, In Review or Resolved. 2. Create a notification row for the faculty when a grievance is raised and for the student when the status changes (the notification service from FR-13 will send the email later). 3. UI: student 'Raise Grievance' button next to a grade and a 'My Grievances' list; faculty 'Grievances' page. 4. Add the one-line req.audit assignment from FR-16 to your write endpoints. |
| Done when | Faculty is notified within 5 minutes of a new grievance. The student sees every status change. |
| Test case(s) | TC-13 |
| Unblocks | - |

### NFR-04 - Maintain 99% System Availability

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 2 / 2 SP |
| GitHub issue | #22 |
| When | Tue 27 Oct. |
| Start only after | Sprint 1 build stable on main. |
| Steps | 1. Deploy the app (backend, frontend, database) to a free host (Render, Railway or similar) or to a college VM with Docker Compose. Use a process manager so it restarts after a crash. 2. Make sure GET /api/v1/health also checks the database connection. 3. Set up a free uptime monitor (for example UptimeRobot) on the health URL and write the URL in the README. |
| Done when | The app is reachable at a public URL, restarts on failure and is monitored. |
| Test case(s) | Analysis (uptime monitoring) |
| Unblocks | SEC-03, NFR-01. |

### NFR-08 - Implement Automatic Backup and Recovery

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 2 / 3 SP |
| GitHub issue | #26 |
| When | Tue 27 Oct. |
| Start only after | NFR-04 (database running on the host). |
| Steps | 1. scripts/backup.sh using pg_dump, run daily by cron or the host's scheduled job. Keep the last 7 backups. 2. scripts/restore.sh restores a backup into a fresh database. 3. Test: back up, delete the test database, restore, and note the time taken (target: under 4 hours; for this project minutes). Save the screenshot or log in docs/test-evidence/. |
| Done when | Daily backup is scheduled and a restore has been tested. |
| Test case(s) | TC-20 |
| Unblocks | - |

### SEC-03 - Enforce HTTPS and TLS 1.2 or Higher

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 2 / 3 SP |
| GitHub issue | #31 |
| When | Wed 28 Oct. |
| Start only after | NFR-04 (deployment). |
| Steps | 1. Use the host's HTTPS (or Nginx with Let's Encrypt). Redirect HTTP to HTTPS. 2. Disable TLS versions below 1.2 (check with testssl.sh or an online SSL test) and save the result. 3. If the host cannot do this for the class demo, run it locally and write a deviation entry. |
| Done when | Plain HTTP is redirected to HTTPS and TLS below 1.2 is refused. |
| Test case(s) | TC-17 |
| Unblocks | - |

### NFR-03 - Support Large Student and Attendance Datasets

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 2 / 2 SP |
| GitHub issue | #21 |
| When | Wed 28 Oct. |
| Start only after | NFR-04. |
| Steps | 1. scripts/generate-load-data.js inserts 10,000 students and 200,000 attendance rows into a separate performance database (never the real seed). 2. Add indexes on attendance_records(enrolment_id, session_date) and students(roll_no). Make list endpoints paginated. 3. Check the main pages still respond within 2 seconds with this data. |
| Done when | The system holds 10,000 students and 200,000 attendance rows and still responds within 2 s. |
| Test case(s) | TC-18 (data for the test) |
| Unblocks | NFR-01. |

### NFR-01 - Meet Performance Target Under Concurrent Load

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 2 / 3 SP |
| GitHub issue | #19 |
| When | Thu 29 Oct. |
| Start only after | NFR-03 data loaded and the app deployed. |
| Steps | 1. Create a JMeter test plan: 200 concurrent users for 10 minutes on a mix of logins, reads and writes. Save it in tests/performance/. 2. Run it and record the 95th percentile response time (target 2 s or less) and the error rate (under 1 %). 3. If the target is missed, tune (indexes, pool size) and run again. If the free host cannot handle 200 users, run locally and write a deviation entry. 4. Save the summary report in docs/perf/. |
| Done when | 95th percentile response time is 2 s or less and the error rate is under 1 %. |
| Test case(s) | TC-18 |
| Unblocks | DEV-02 (result for the log). |

### NFR-02 - Generate Class Reports Within 3 Seconds

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Kushita / Sprint 2 / 2 SP |
| GitHub issue | #20 |
| When | Thu 29 Oct. |
| Start only after | FR-14 and NFR-03 data. |
| Steps | 1. With 100 students in a class, generate the class report as PDF and CSV ten times and record the times. 2. If any run takes more than 3 seconds, tell Nidhi (FR-14 owner) and add an index or query fix together. 3. Save the timing table in docs/perf/. |
| Done when | A class report for up to 100 students is generated and exported within 3 seconds. |
| Test case(s) | TC-12 |
| Unblocks | DEV-02. |

## 7.3 Nagashree

Sprint 1: DEV-01 (3), FR-06 (5), FR-08 (5), FR-09 (2) = 15 SP.   Sprint 2: FR-07 (2), FR-13 (5), NFR-09 (2), NFR-06 (2), NFR-07 (5), DEV-02 (5) = 21 SP.

Your first message to Claude (after the Master Prompt):

I am Nagashree from TEAM-E12. I attached the Team Playbook, SRS, SAD and Test Plan. My tasks are in Section 7.3. Start with DEV-01 (GitHub Actions CI), then FR-06 (enter marks and letter grades). Give me the files, code, tests, how to run them, and the commit message and PR description.

### Nagashree - Sprint 1 task cards

### DEV-01 - Configure GitHub Actions CI Workflow

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 1 / 3 SP |
| GitHub issue | #38 |
| When | Mon 19 Oct, morning. PR by 12 noon. |
| Start only after | DEV-04 (the project must have package.json files). |
| Steps | 1. Create .github/workflows/ci.yml (sample in Appendix D): runs on every pull request and on pushes to main. Backend job: npm ci, lint, tests. Frontend job: npm ci, lint, build. 2. Add .github/pull_request_template.md (text in Appendix D) if Monika has not already added it. 3. Optional if time allows: a workflow that adds new PRs to the GitHub Project automatically. 4. Add the CI status badge to the README and take a screenshot of one green run for the evidence folder. 5. Open the PR. After the merge every later PR must show the CI check. |
| Done when | CI runs on every PR and shows pass or fail. |
| Test case(s) | Part-2 Sprint 1(b) |
| Unblocks | The CI check on every PR from Mon afternoon. |

### FR-06 - Enter Marks and Compute Letter Grades

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 1 / 5 SP |
| GitHub issue | #7 |
| When | Mon 19 Oct (logic and tests) to Tue 20 Oct (endpoint and page). |
| Start only after | DEV-04 seed data. SEC-02 requireRole (Mon 6 PM) for the final wiring. |
| Steps | 1. services/grade.js: letterGrade(marks) using a grading scale constant in config (90 and above A+, 80 A, 70 B+, 60 B, 50 C, 40 D, below 40 F). Agree the scale with the team and write it in the README. 2. POST /api/v1/courses/:id/grades (FACULTY assigned to the course): marks must be a number from 0 to 100. Check the faculty is assigned to the course and the student is enrolled, otherwise 403 or 404. Save inside one database transaction. 3. Faculty page 'Enter Marks': choose course, see the student table, type marks, save. Put it in frontend/src/pages/faculty/. 4. Unit tests: 78 is saved with letter grade, and 105, -5 and 'abc' are rejected with 400. Test: faculty A cannot post to faculty B's course (403). |
| Done when | Out-of-range or non-numeric marks are rejected. Entry for an unassigned course returns HTTP 403. Letter grade follows the scale. |
| Test case(s) | TC-05, TC-06 |
| Unblocks | FR-07, FR-10 (real data), FR-14. |

### FR-08 - Mark and Edit Student Attendance

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 1 / 5 SP |
| GitHub issue | #9 |
| When | Wed 21 Oct. |
| Start only after | FR-06 (same pattern). |
| Steps | 1. POST /api/v1/courses/:id/attendance with { session_date, records: [{ student_id, status }] } where status is Present, Absent or Late. Save in one transaction. One row per student per session date. 2. PUT /api/v1/attendance/:id: FACULTY may edit only within 24 hours of marked_at, ADMIN may edit at any time. Otherwise 403. 3. Faculty page 'Mark Attendance' with a date picker and a Present/Absent/Late selector per student. 4. Tests: normal save, duplicate session date, edit within 24 h, edit after 24 h (rejected). |
| Done when | Edits by Faculty after 24 hours are rejected. Only an Administrator may edit later. |
| Test case(s) | TC-07 |
| Unblocks | FR-09, FR-10, FR-13. |

### FR-09 - Calculate Attendance Percentage

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 1 / 2 SP |
| GitHub issue | #10 |
| When | Thu 22 Oct. |
| Start only after | FR-08. |
| Steps | 1. services/attendance.js: percentage = (Present + Late) / total sessions x 100, rounded to 1 decimal. Write this rule in the README (Late counts as attended; it is in the deviations log as DV-04). 2. GET /api/v1/students/:id/attendance-summary returns course-wise and overall percentage (mount it in student-attendance.routes.js). 3. Show the percentage on the faculty attendance page and let Nidhi use the endpoint for the student page. 4. Unit tests: 8 Present of 10 sessions equals 80.0. |
| Done when | Displayed percentage equals the manual calculation to 1 decimal place and refreshes within 2 s. |
| Test case(s) | TC-07 |
| Unblocks | FR-10 (attendance view), FR-13. |

### Nagashree - Sprint 2 task cards

### FR-07 - Correct Marks with Mandatory Reason

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 2 / 2 SP |
| GitHub issue | #8 |
| When | Mon 26 Oct. |
| Start only after | FR-06. |
| Steps | 1. PATCH /api/v1/courses/:id/grades/:gradeId requires a reason of at least 5 characters. Without it return 400. 2. Store old marks, new marks, reason, changed_by and time in grade_history (and set req.audit for FR-16). 3. Add an 'Edit with reason' dialog to the faculty marks page. 4. Tests: correction without a reason is rejected; with a reason it is saved with the old and new value. |
| Done when | Update without a reason is rejected. Old value, new value and reason are stored. |
| Test case(s) | TC-05 |
| Unblocks | - |

### FR-13 - Notify Students and Parents of Low Attendance

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 2 / 5 SP |
| GitHub issue | #14 |
| When | Mon 26 Oct to Tue 27 Oct. |
| Start only after | FR-09. |
| Steps | 1. services/notification.js: after attendance is saved, compute the percentage. If it falls below the threshold (settings table, default 75) and no alert was already sent for this crossing, create notifications for the student and the linked parent. 2. Send the email with Nodemailer using a sandbox SMTP account (for example Mailtrap). Keep credentials in .env. If email is not possible, keep in-app notifications and write a deviation entry. 3. GET /api/v1/notifications (own notifications) and PUT /api/v1/settings/attendance-threshold (ADMIN) with a small admin settings page. 4. Tests: attendance goes from 76 % to 74 %, one notification is created; saving again does not create a second one. |
| Done when | Notification is generated within 5 minutes and sent only once per threshold crossing. |
| Test case(s) | TC-11 |
| Unblocks | FR-15 email sending. |

### NFR-09 - Ensure Grade and Attendance Data Integrity

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 2 / 2 SP |
| GitHub issue | #27 |
| When | Tue 27 Oct. |
| Start only after | FR-06 and FR-08 merged. |
| Steps | 1. Write an automated test that forces an error in the middle of a grade save and an attendance save, and checks that no partial row remains. 2. Do the manual version from the Test Plan: stop the server during a write and check the database. 3. Save the result in docs/test-evidence/. |
| Done when | Every write to grade and attendance data is atomic. No partial record remains after a failure. |
| Test case(s) | TC-20 |
| Unblocks | - |

### NFR-06 - Ensure Browser Compatibility and Responsive Design

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 2 / 2 SP |
| GitHub issue | #24 |
| When | Wed 28 Oct. |
| Start only after | UI pages complete (Tue 27 Oct). |
| Steps | 1. Open the main flows of each role in the latest Chrome, Firefox and Edge and at a 360 px width. 2. Write the results in a table (browser, page, result) in docs/test-evidence/. 3. Fix layout problems yourself in small PRs or send them to the page owner. |
| Done when | The system works on the latest two versions of Chrome, Firefox and Edge and on screens 360 px wide or larger. |
| Test case(s) | TC-19 |
| Unblocks | - |

### NFR-07 - Ensure Maintainable Code and API Documentation

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 2 / 5 SP |
| GitHub issue | #25 |
| When | Wed 28 Oct. |
| Start only after | Features merged (Mon to Tue). |
| Steps | 1. Run the test coverage report (jest --coverage). Add tests until the service layer has at least 70 % statement coverage. 2. Write docs/api/openapi.yaml (OpenAPI 3.0) for every endpoint in Appendix A. Ask Claude to draft it from the route files, then check it yourself. 3. Link the OpenAPI file and the coverage figure in the README. |
| Done when | At least 70 % statement coverage in the service layer and an OpenAPI 3.0 document exist. |
| Test case(s) | Inspection (coverage report, OpenAPI file) |
| Unblocks | DEV-03. |

### DEV-02 - Verify Requirements Against the Test Plan

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nagashree / Sprint 2 / 5 SP |
| GitHub issue | #39 |
| When | Thu 29 Oct (morning to evening). |
| Start only after | Feature complete (Wed 28 Oct 6 PM). |
| Steps | 1. Open the Test Plan Section 8 and run TC-01 to TC-17 one by one on the deployed or local build, using the steps and test data in the table. 2. Record in docs/test-results.md (or an Excel sheet): TC id, date, tester, Pass / Fail / Blocked, evidence (screenshot or curl output). 3. Raise a GitHub issue with the label 'bug' for every failure and tell the owner. Retest after the fix. 4. Add the results of TC-18, TC-19 and TC-20 from Kushita, Nidhi and your own NFR work. |
| Done when | All 20 test cases have a recorded result and every failure has an issue. |
| Test case(s) | TC-01 to TC-20 |
| Unblocks | DEV-03 and the final demo. |

## 7.4 Nidhi

Sprint 1: UI-01 (5), SEC-08 (3), FR-10 (3), FR-17 (3), DEV-05 (2) = 16 SP.   Sprint 2: FR-14 (5), FR-11 (2), FR-12 (3), NFR-05 (2), NFR-10 (3), DEV-03 (3), DEV-06 (2) = 20 SP.

Your first message to Claude (after the Master Prompt):

I am Nidhi from TEAM-E12. I attached the Team Playbook, SRS, SAD and Test Plan. My tasks are in Section 7.4. Start with UI-01 (login page and role-based dashboards, using a mock login until the real one is merged). Give me the files, code, how to run and test it, and the commit message and PR description.

### Nidhi - Sprint 1 task cards

### UI-01 - Build Login Page and Role-Based Dashboards

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 1 / 5 SP |
| GitHub issue | NEW (number given when created) |
| When | Mon 19 Oct to Tue 20 Oct. The shell must be merged by Tue 6 PM. |
| Start only after | DEV-04 (frontend folder). FR-01 only for final integration, so start with a mock. |
| Steps | 1. Set up routes: /login, /change-password, /admin, /faculty, /student, /parent. Build an AuthContext (token and role kept in sessionStorage), a ProtectedRoute that checks the role, and api/client.js that sends 'Authorization: Bearer' and redirects to /login on 401. 2. Build the layout with a sidebar. Keep the menu items for each role in ONE config file (frontend/src/config/menu.js) so teammates add their pages by adding one line each. 3. Build the Login page (error message on failure) and the Change Password page, shown when the login response has mustChangePassword = true. 4. Create four dashboard pages with placeholder cards. Make the layout work at 360 px width (this is also the base for NFR-06). 5. Use a mock login until Monika merges FR-01 (Tue evening), then switch to the real API and test all four roles on Wed. |
| Done when | Logging in as each seeded role lands on the correct dashboard. A wrong-role URL redirects away. The layout works on a 360 px screen. |
| Test case(s) | TC-01, TC-19 |
| Unblocks | Kushita, Nagashree and Nidhi pages (they add pages from Wed). |

### SEC-08 - Enforce Object-Level Authorization

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 1 / 3 SP |
| GitHub issue | #36 |
| When | Tue 20 Oct. |
| Start only after | SEC-04 (req.user). |
| Steps | 1. Create backend/src/middleware/ownership.js with canAccessStudent(user, studentId) and an express middleware requireStudentAccess. ADMIN: yes. STUDENT: only the student row linked to their own user. PARENT: only students linked in parent_links. Anything else: 403 with no data. 2. Unit tests with two students and one parent: own record allowed, another student's record 403, linked child allowed, unlinked child 403. 3. Tell Kushita and Nagashree it is merged so GET /students/:id and the attendance summary can use it. |
| Done when | Changing the student id in a request returns HTTP 403 and no data. |
| Test case(s) | TC-08, TC-10 |
| Unblocks | FR-10, FR-11, FR-12. |

### FR-10 - View Own Grades and Attendance

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 1 / 3 SP |
| GitHub issue | #11 |
| When | Wed 21 Oct to Thu 22 Oct. |
| Start only after | SEC-08. FR-06 and FR-08 for real data (use seed data until they merge). |
| Steps | 1. GET /api/v1/students/:id/grades (mount in student-records.routes.js) with requireStudentAccess. Returns course-wise marks and letter grades. 2. Student pages 'My Grades' and 'My Attendance' (the attendance numbers come from Nagashree's attendance-summary endpoint). Add them to the student menu. 3. Test: a student sees only their own data; another id returns 403. |
| Done when | A request for another student's data returns HTTP 403 and no data. |
| Test case(s) | TC-08 |
| Unblocks | The Sprint 1 demo flow. |

### FR-17 - Update Student Contact Details

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 1 / 3 SP |
| GitHub issue | #18 |
| When | Thu 22 Oct. |
| Start only after | FR-10. |
| Steps | 1. PATCH /api/v1/students/me/contact (STUDENT only). Accept only phone, email and address. Any other field (marks, roll_no, semester) is rejected with 403. 2. Student page 'My Profile' with an edit form. 3. Tests: contact saved and shown immediately; sending marks in the body is rejected. |
| Done when | Contact changes are saved and shown immediately. Any attempt to modify marks or attendance is rejected with HTTP 403. |
| Test case(s) | TC-08 |
| Unblocks | - |

### DEV-05 - Record and Upload Sprint 1 Demo Video

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 1 / 2 SP |
| GitHub issue | NEW (number given when created) |
| When | Fri 23 Oct, after the 12 noon code freeze. |
| Start only after | All Sprint 1 PRs merged and Monika has tagged sprint-1. |
| Steps | 1. Pull main into a clean folder and run the app from the README to prove it works from scratch. 2. Follow the 1-minute script in Section 9.1 and record the screen with audio. 3. Save as demo/sprint1.mp4. If the file is larger than 100 MB, compress it or upload to Drive and put the link in demo/README.md. 4. Upload through a PR 'DEV-05: Add Sprint 1 demo video' that closes this issue. |
| Done when | A 1-minute video of the working product is in the repo. |
| Test case(s) | Part-2 Sprint 1(g, h) |
| Unblocks | Sprint 1 submission. |

### Nidhi - Sprint 2 task cards

### FR-14 - Generate and Export Class and Student Reports

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 2 / 5 SP |
| GitHub issue | #15 |
| When | Mon 26 Oct to Tue 27 Oct. Export module PR first, by Mon evening. |
| Start only after | FR-06, FR-08, FR-09 (data to report). |
| Steps | 1. Build services/export.js: generatePdf(title, rows) with pdfkit and generateCsv(rows). Open a small PR for this first, because FR-11 reuses it. 2. GET /api/v1/reports/class/:courseId (ADMIN all, FACULTY own course) and GET /api/v1/reports/student/:id, both with ?format=pdf or csv. 3. Frontend 'Reports' page for admin and faculty with filters and download buttons. 4. Tests: totals in the report equal totals in the database. |
| Done when | A report for up to 100 students is displayed and exported within 3 s. Totals equal database totals. |
| Test case(s) | TC-12 |
| Unblocks | FR-11 and NFR-02. |

### FR-11 - Download Student Report Card as PDF

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 2 / 2 SP |
| GitHub issue | #12 |
| When | Tue 27 Oct. |
| Start only after | FR-14 export module and SEC-08. |
| Steps | 1. GET /api/v1/students/:id/report-card returns a PDF with name, roll number, course-wise marks, letter grades and attendance. Use requireStudentAccess. 2. Add a 'Download Report Card' button on the student dashboard. 3. Test the 5-second limit with the seed data. |
| Done when | PDF is generated within 5 s and contains name, roll number, course-wise marks, grades and attendance. |
| Test case(s) | TC-09 |
| Unblocks | - |

### FR-12 - View Linked Student Grades and Attendance

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 2 / 3 SP |
| GitHub issue | #13 |
| When | Wed 28 Oct. |
| Start only after | SEC-08 and the parent_links seed data. |
| Steps | 1. GET /api/v1/parents/me/students returns the linked students. Reuse the grades and attendance-summary endpoints (they already allow a linked parent through requireStudentAccess). 2. Build the parent pages: linked students list, then grades and attendance for the chosen student. 3. Test: the linked student's data is shown and an unlinked student id returns 403. |
| Done when | A request for an unlinked student returns HTTP 403 and no data. |
| Test case(s) | TC-10 |
| Unblocks | - |

### NFR-05 - Ensure Faculty Usability

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 2 / 2 SP |
| GitHub issue | #23 |
| When | Thu 29 Oct. |
| Start only after | UI complete. |
| Steps | 1. Make a table of every core function for each role and count the clicks from the dashboard. Fix anything above 3 clicks. 2. Ask one person outside the team to enter marks for a class without help and time it (target under 10 minutes). 3. Save the table and the result in docs/test-evidence/. |
| Done when | Every core function is reachable within 3 clicks and a first-time user can enter marks within 10 minutes. |
| Test case(s) | TC-19 |
| Unblocks | - |

### NFR-10 - Meet Accessibility Requirements

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 2 / 3 SP |
| GitHub issue | #28 |
| When | Thu 29 Oct. |
| Start only after | UI complete. |
| Steps | 1. Run Lighthouse and axe on the login page and each dashboard. Save the reports. 2. Fix labels on inputs, colour contrast, keyboard navigation and alt text until there are zero critical violations. 3. Run the scan again and save the final report. |
| Done when | Main pages meet WCAG 2.1 AA with zero critical violations in the automated scan. |
| Test case(s) | TC-19 |
| Unblocks | - |

### DEV-03 - Complete Project Documentation

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 2 / 3 SP |
| GitHub issue | #40 |
| When | Thu 29 Oct to Fri 30 Oct, finished by 3 PM. |
| Start only after | Features complete. DEV-02 results and DEV-07 deviations are inputs. |
| Steps | 1. Write the README: overview, stack, setup, environment variables, scripts, test accounts, how to run tests, link to the OpenAPI file. 2. Update the SRS, SAD and Test Plan only where the product differs (mark changed pages and bump the version to 1.1 with a change note). 3. Write a short user guide with one screenshot per role. 4. Check the docs folder is tidy: SRS, SAD, Test Plan, DEVIATIONS.md, test results, performance and security reports. |
| Done when | README, updated documents and user guide are in the repo. |
| Test case(s) | Part-2 Sprint 2(c) |
| Unblocks | DEV-08 freeze. |

### DEV-06 - Record and Upload Sprint 2 Demo Video

| Field | Detail |
| --- | --- |
| Owner / Sprint / Points | Nidhi / Sprint 2 / 2 SP |
| GitHub issue | NEW (number given when created) |
| When | Fri 30 Oct, after the final fixes. |
| Start only after | Features complete and DEV-03 done. |
| Steps | 1. Follow the 2-minute script in Section 9.2 on a clean run of the final build. 2. Save as demo/sprint2.mp4 (or a link in demo/README.md) and upload through a PR. 3. Tell Monika so the freeze (DEV-08) can start. |
| Done when | A 2-minute video of the working product is in the repo. |
| Test case(s) | Part-2 Sprint 2(b) |
| Unblocks | DEV-08. |

# 8. Team Lead Checklists (Monika)

## 8.1 Backlog on GitHub, today (Mon 12 Oct), in this order

The spreadsheet Part2_Sprint_Backlog_TEAM-E12_v2.xlsx has the exact values (Backlog, Title Fixes and Change Log tabs). Work through it step by step and do not delete any issue.

| Step | Action | Check |
| --- | --- | --- |
| 1 | Repo Settings, Collaborators: invite Kushita, Nagashree and Nidhi. They accept. | All three appear as collaborators |
| 2 | Rename issues #4 to #40: remove the leading 'Title: '. #1 and #2 are already right. | All titles start with the ID, for example 'FR-03: ...' |
| 3 | Create the 6 new issues: UI-01, DEV-04, DEV-05, DEV-06, DEV-07, DEV-08 (titles in the Title Fixes tab). Add them to the Project. | 45 items on the board |
| 4 | Update Story Points and Sprint on the 22 changed issues (Change Log tab). | Sprint 1 = 64, Sprint 2 = 82, total = 146 |
| 5 | Assign every issue to its owner (Backlog tab, column J). | No issue without an assignee |
| 6 | Repo Projects tab: make sure the project is linked. Add the instructor as collaborator or make it visible. Add a Board view (To Do, In Progress, In Review, Done). | Project shows under the repo |
| 7 | Settings, Branches: protect main (require a pull request and 1 approval). Copy the PR template into .github. | Direct push to main is blocked |
| 8 | Issue #3 is missing from the list: check it is not a stray issue. | Explained or removed |

## 8.2 PR review checklist

- Does the PR close one issue and meet that card's 'Done when'? Is CI green?

- Is it inside the owner's files (Section 3.3)? No secrets, no logging of passwords, no commented-out code?

- Are SQL queries parameterised, input validated, and grade/attendance writes in a transaction?

- Is there at least one test and evidence in the description? Is anything different from the SRS, SAD or Test Plan written in DEVIATIONS.md?

## 8.3 End-of-sprint checklist

- Sprint 1 (Fri 23 Oct): everything merged, README run steps tested from a clean clone, tag sprint-1, 1-minute video uploaded, board statuses correct, deviations log updated.

- Sprint 2 (Fri 30 Oct): all issues Done or explained, DEV-03 and DEV-07 complete, 2-minute video uploaded, clean-clone test, main protected, tag v1.0, board and CI screenshots saved.

# 9. Demo Video Scripts

Record the screen with your voice. Use the seeded test accounts. Do a dry run first. Keep to the time limit.

## 9.1 Sprint 1: 1-minute video (Nidhi)

| Time | Show | Say |
| --- | --- | --- |
| 0:00 - 0:08 | Title and repo name | Student Record System by TEAM-E12, Sprint 1. |
| 0:08 - 0:20 | Log in as admin, create a student, show the list | Admin logs in and creates a student record. Validation rejects a duplicate roll number. |
| 0:20 - 0:35 | Log in as faculty, enter marks, mark attendance | Faculty sees only assigned courses, enters marks with automatic letter grade, and marks attendance. |
| 0:35 - 0:48 | Log in as student, open My Grades and My Attendance; try another student's id (403) | The student sees only their own data. Another student's record is blocked. |
| 0:48 - 1:00 | GitHub: green CI, merged PRs, project board | Work is delivered through reviewed pull requests with CI. Deviations are logged. |

## 9.2 Sprint 2: 2-minute video (Nidhi)

| Time | Show | Say |
| --- | --- | --- |
| 0:00 - 0:10 | Title, deployed URL | Final Student Record System, running at this URL. |
| 0:10 - 0:35 | Faculty corrects marks with a reason; attendance drops below 75 %; notification appears | Corrections need a reason. Low attendance sends one alert to student and parent. |
| 0:35 - 1:00 | Student downloads the report card; parent logs in and sees the linked child | Report card PDF in seconds. Parents see only their linked student. |
| 1:00 - 1:20 | Admin: class report export (PDF and CSV), audit log page | Reports export quickly. Every change is in an append-only audit log. |
| 1:20 - 1:45 | Security: 5 wrong logins lock the account, 403 on wrong role, rate limit 429, HTTPS padlock | Lockout, role checks, rate limiting and HTTPS are in place. |
| 1:45 - 2:00 | GitHub board all Done, CI green, v1.0 tag, DEVIATIONS.md | Everything is delivered and tagged v1.0. Deviations are documented. |

# 10. Deviations Log

The teacher expects every difference from the submitted SRS, SAD and Test Plan to be written down and explained in the final demo. Monika owns docs/DEVIATIONS.md. Everyone adds an entry the moment they decide to do something differently. Table columns: ID, document and section, what was submitted, what was built, reason, impact.

## 10.1 Differences already known (confirm or remove each one)

| ID | Document and section | Submitted | Planned in this playbook | Reason |
| --- | --- | --- | --- | --- |
| DV-01 | SAD Section 8 (SD-2) and Section 9 | Sequence diagram uses POST /api/v1/grades; API table uses POST /api/v1/courses/{id}/grades | Use the API table path | The course id is needed for the faculty-assignment check |
| DV-02 | SRS FR-05 and SAD Section 11 | FR-05 says one or more faculty per course; the schema has a single faculty_id | One faculty per course | Simpler schema; meets the acceptance criterion |
| DV-03 | SAD Section 11 tables | Simplified table list | Extra tables and columns: grade_history, notifications, settings, alert state, student phone/email/address | Needed for FR-07, FR-13, FR-17 |
| DV-04 | SRS FR-09 | Late is not defined | Late counts as attended | Clarification |
| DV-05 | SRS FR-13 and SAD C12 | E-mail/SMS gateway | Sandbox e-mail plus in-app notifications; no SMS | No paid gateway |
| DV-06 | Test Plan TC-17, TC-18 | TLS on a deployed server; 200 users | Depends on the free host; reduce or run locally if needed | Hosting limits |
| DV-07 | SAD Section 9 | Representative endpoints only | Extra endpoints (auth/me, change-password, faculty, courses, notifications, settings) | Needed to complete the use cases |

# 11. Risks and Fallbacks

| Risk | Fallback |
| --- | --- |
| Skeleton (DEV-04) is late | Monika pairs with Kushita on Wednesday. Nobody starts Sprint 1 work early; the dry-run week is the buffer. |
| Auth middleware (SEC-04, SEC-02) late on Monday | Others use a temporary dev-only role header, removed before the Friday freeze. |
| A member is absent | Backup owner (Section 3.2) takes the open issues the same day; Monika updates the board. |
| Free hosting cannot deploy or handle load | Demo locally from a clean clone, run JMeter locally, and add a deviation entry. |
| E-mail sending does not work | Keep in-app notifications and log a deviation. |
| Merge conflicts | Follow file ownership (Section 3.3), pull main before each task, keep PRs small, ask Claude to explain the conflict markers. |
| Running out of time in Sprint 2 | Order of importance: FR-16 audit, FR-14 reports, FR-13 notification, FR-15 grievances. Security and test evidence (DEV-02) must not be dropped. |

# Appendix A. API Contract

| Method and path | Who can call | Issue | Owner |
| --- | --- | --- | --- |
| POST /api/v1/auth/login | Public | FR-01 | Monika |
| GET /api/v1/auth/me | Any logged-in user | FR-01 | Monika |
| POST /api/v1/auth/change-password | Any logged-in user | FR-01 | Monika |
| GET /api/v1/health | Public | DEV-04 | Kushita |
| POST /api/v1/students | ADMIN | FR-02 | Kushita |
| GET /api/v1/students, GET /api/v1/students/:id | ADMIN; STUDENT own; PARENT linked (SEC-08) | FR-02 | Kushita |
| PUT /api/v1/students/:id, PATCH /api/v1/students/:id/deactivate | ADMIN | FR-03 | Kushita |
| PATCH /api/v1/students/me/contact | STUDENT | FR-17 | Nidhi |
| POST /api/v1/faculty, PATCH /api/v1/faculty/:id, PATCH /api/v1/faculty/:id/deactivate | ADMIN | FR-04 | Kushita |
| POST /api/v1/courses, GET /api/v1/courses, PUT /api/v1/courses/:id/faculty, POST /api/v1/courses/:id/enrolments | ADMIN (GET: FACULTY sees assigned only) | FR-05 | Kushita |
| POST /api/v1/courses/:id/grades | FACULTY assigned to the course | FR-06 | Nagashree |
| PATCH /api/v1/courses/:id/grades/:gradeId | FACULTY assigned, reason required | FR-07 | Nagashree |
| POST /api/v1/courses/:id/attendance, PUT /api/v1/attendance/:id | FACULTY assigned (edit within 24 h); ADMIN any time | FR-08 | Nagashree |
| GET /api/v1/students/:id/attendance-summary | ADMIN; STUDENT own; PARENT linked | FR-09 | Nagashree |
| GET /api/v1/students/:id/grades | ADMIN; STUDENT own; PARENT linked | FR-10 | Nidhi |
| GET /api/v1/students/:id/report-card | ADMIN; STUDENT own; PARENT linked | FR-11 | Nidhi |
| GET /api/v1/parents/me/students | PARENT | FR-12 | Nidhi |
| GET /api/v1/notifications, PUT /api/v1/settings/attendance-threshold | Own notifications; ADMIN for the setting | FR-13 | Nagashree |
| GET /api/v1/reports/class/:courseId, GET /api/v1/reports/student/:id (?format=pdf or csv) | ADMIN; FACULTY own course | FR-14 | Nidhi |
| POST /api/v1/grievances, GET /api/v1/grievances, PATCH /api/v1/grievances/:id | STUDENT raises; FACULTY responds | FR-15 | Kushita |
| GET /api/v1/audit-logs | ADMIN read-only | FR-16 | Monika |

# Appendix B. Database Tables

| Table | Columns |
| --- | --- |
| users | id, username (unique), password_hash, role, name, email, must_change_password, failed_attempts, locked_until, is_active |
| students | id, user_id, roll_no (unique), name, dob, department, semester, phone, email, address, guardian_contact, is_active |
| faculty | id, user_id, name, department, is_active |
| courses | id, code (unique), name, semester, faculty_id |
| enrolments | id, student_id, course_id (unique together) |
| grades | id, enrolment_id (unique), marks, letter_grade, updated_by, updated_reason, updated_at |
| grade_history | id, grade_id, old_marks, new_marks, reason, changed_by, changed_at |
| attendance_records | id, enrolment_id, session_date, status, marked_by, marked_at (enrolment_id + session_date unique) |
| parent_links | id, parent_user_id, student_id |
| grievances | id, student_id, target_type, target_id, reason, status, response, raised_at, resolved_at |
| notifications | id, user_id, type, message, created_at, sent_at, is_read |
| attendance_alert_state | id, enrolment_id, below_threshold (stops duplicate alerts) |
| settings | key, value (attendance_threshold = 75) |
| audit_log | id, user_id, role, action, entity, entity_id, old_value, new_value, created_at (append-only) |

# Appendix C. Test Cases: Who Checks What

Check your own test cases by hand before opening the PR. Nagashree runs the formal pass (DEV-02) and records results; TC-18 to TC-20 results come from the NFR owners.

| Test case | Verifies | Checked first by | Formal run |
| --- | --- | --- | --- |
| TC-01 | Login for 4 roles, password hashes (FR-01, SEC-01) | Monika | Nagashree |
| TC-02 | Lockout after 5 failures (SEC-05) | Monika | Nagashree |
| TC-03 | Student create, update, deactivate (FR-02, FR-03) | Kushita | Nagashree |
| TC-04 | Faculty account and course assignment (FR-04, FR-05) | Kushita | Nagashree |
| TC-05 | Marks entry and correction (FR-06, FR-07) | Nagashree | Nagashree |
| TC-06 | Faculty cannot grade another faculty's course (SEC-02) | Monika and Nagashree | Nagashree |
| TC-07 | Attendance and percentage (FR-08, FR-09) | Nagashree | Nagashree |
| TC-08 | Student own data, profile, 403 on other student (FR-10, FR-17, SEC-08) | Nidhi | Nagashree |
| TC-09 | Report card PDF (FR-11) | Nidhi | Nagashree |
| TC-10 | Parent sees linked child only (FR-12) | Nidhi | Nagashree |
| TC-11 | Low-attendance alert (FR-13) | Nagashree | Nagashree |
| TC-12 | Reports within 3 seconds (FR-14, NFR-02) | Nidhi and Kushita | Nagashree |
| TC-13 | Grievance flow (FR-15) | Kushita | Nagashree |
| TC-14 | Audit log and append-only (FR-16, SEC-07) | Monika | Nagashree |
| TC-15 | SQL injection and XSS, ZAP scan (SEC-06) | Monika | Nagashree |
| TC-16 | Token expiry and tampering (SEC-04) | Monika | Nagashree |
| TC-17 | HTTPS, TLS version, rate limit (SEC-03, SEC-09) | Kushita and Monika | Nagashree |
| TC-18 | 200 users, 10,000 students (NFR-01, NFR-03) | Kushita | Result copied into the log |
| TC-19 | Browsers, 3 clicks, accessibility (NFR-05, NFR-06, NFR-10) | Nidhi and Nagashree | Result copied into the log |
| TC-20 | Backup and restore, atomic writes (NFR-08, NFR-09) | Kushita and Nagashree | Result copied into the log |

# Appendix D. Templates

## D.1 Pull request template (.github/pull_request_template.md)

## What this PR does

Closes #<issue number>

## How I tested it

(paste curl output or a screenshot)

## Checklist

- [ ] "Done when" of the task card is met

- [ ] Unit tests added, CI is green

- [ ] SQL parameterised, input validated, transaction used for grades/attendance

- [ ] No secrets in the code

- [ ] Differences from SRS/SAD/Test Plan added to docs/DEVIATIONS.md

## D.2 CI workflow (.github/workflows/ci.yml), sample for DEV-01

name: CI

on:

pull_request:

branches: [main]

push:

branches: [main]

jobs:

backend:

runs-on: ubuntu-latest

defaults:

run:

working-directory: backend

steps:

- uses: actions/checkout@v4

- uses: actions/setup-node@v4

with:

node-version: 20

cache: npm

cache-dependency-path: backend/package-lock.json

- run: npm ci

- run: npm run lint --if-present

- run: npm test --if-present

frontend:

runs-on: ubuntu-latest

defaults:

run:

working-directory: frontend

steps:

- uses: actions/checkout@v4

- uses: actions/setup-node@v4

with:

node-version: 20

cache: npm

cache-dependency-path: frontend/package-lock.json

- run: npm ci

- run: npm run lint --if-present

- run: npm run build

## D.3 Daily standup message

Done yesterday: FR-06 logic and unit tests (PR #12 open)

Doing today: FR-06 endpoint and Enter Marks page

Blocked by: waiting for Monika's requireRole middleware (SEC-02)

## D.4 docs/DEVIATIONS.md table

| ID | Document and section | Submitted | Built | Reason | Impact | Added by |

|----|----------------------|-----------|-------|--------|--------|----------|

## D.5 Commit message examples

FR-06: validate marks and compute letter grade (#7)

SEC-04: add JWT sign and verify utilities (#32)

DEV-01: add GitHub Actions CI workflow (#38)

fix: return 403 when faculty is not assigned to the course (#7)